## Ark1
Lofthus frukt og saft Website Project |  |  | PLAN |  |  |  |  | DESIGN |  |  |  |  | BUILD |  |  |  |  | LAUNCH
ACTIVITIES | RESOURCES | PROGRESS | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | 2019-08-12 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | 2019-08-19 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | 2019-08-26
Client meeting | Frontend developer | 0% | Signing contract - confirming goals for the site - client contact |  |  |  |  | Contact with client |  |  |  |  | Contact with client |  |  |  |  | Contact with client
Project meeting | Frontend deleloper Content developer | 0% | Planning the Project
Research | Frontend developer Content developer | 0% | Get insporation from other projects
Strategic planning | Frontend developer Content developer | 0% |  | Planning how to reach the goals for the site
Site Outline | Frontend developer Content developer Developer | 0% |  |  | Planning content and outline the site
Site Structure | Frontend developer Developer | 0% | [5 empty] | Give the site structure
Text content | Content developer Copywriter | 0% | [5 empty] | Producing text for site and action buttons |  | for products
Style tiles / Wireframes | Frontend developer | 0% | [7 empty] | Style tiles for the client- typografi, color, visual elements |  |  | Wireframes
Images | Photographer | 0% | [7 empty] | Photoshoot for the site images and products for the webshop |  |  | Photoshoot of the employees
UX-UI planning/testing | Frontend developer Content developer | 0% | [11 empty] | Plan for UX and UI, then do testing
Coding | Frontend developer Developer | 0% | [11 empty] | Coding the site, front and backend |  |  |  | Coding the site / | Copyright
UX-UI testing | Frontend developer Content developer | 0% | [16 empty] | UX-UI testing
Browser testing | Developer | 0% | [16 empty] | Testing the site on different browsers
Validating | Developer | 0% | [17 empty] | Checking the code
Refinement | Frontend developer Content developer Developer | 0% | [18 empty] | Search optimize site
Launch | Frontend developer Content developer Developer | 0% | [19 empty] | Launching website | TOTAL
|  | Hours | 16 | 16 | 20 | 20 | 20 | 28 | 24 | 28 | 16 | 16 | 16 | 24 | 25 | 25 | 16 | 16 | 24 | 24 | 24 | 12 | 410
|  | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 20